ROLLESTON ON DOVE PARISH COUNCIL

PARISH PLAN STATUS JULY 2007

Action						Status

1.	Improved facilities at Elizabeth Ave			Parents waiting area with benches 			Playing Field.					completed. Additional access path from 								Beacon Road completed.  Constantly 									looking to improve play equipment.

2.	Improve access at Elizabeth Ave			As above.

Playing Field.

3.	Restoration of street scene in Brookside			Some setts re-laid restoration of verges not								complete. Waiting for development to finish.

4.	Progressive introduction of wildflowers			further planting has been completed.  Additional

To Brook Hollows and The Croft.			Spring bulbs planted by the Village Gateways.

5.	Co-operation with neighbouring parishes.		The local Parish Council Chairmen meet 								regularly.  All PC’s are invited to attend ESBC 								Forum meeting.

6.	Long term aim of single site new school.		Have met with SCC who has advised two 								issues, being funding and available land.

7.	Carry out survey of youth facilities.			Initial survey completed.  Appendix to Parish 								Plan completed. A grant application is still in the 								process of being compiled to finance church hall 								improvements to include internet café facilities.

8.	Set up Youth Club if desirable. Introduce		A Youth Club is still considered not appropriate.

Facilities for young people.				Understand from ESBC that Junior Play Area on 								the Westbury Homes development is near 								completion.

9.	Drain Craythorne Field.				Main drain completed.  Annual verti-drainage – 								ongoing.  Reports received that the drainage is 								greatly improved.

10.	Introduce kissing gates on footpaths for 		Ongoing.  Three have been introduced on 		less able access.					footpath	14. New gates have been introduced on 								footpath 7.

11.	Consider a pavement for Anslow Lane.			Have lobbied County Council and nothing more 								can be done.

12.	Consider the future for the Jinny Trail to cyclists.		On the agenda to be discussed in further detail.

13.	Introduce all weather paths from			Still being considered following a reply from the

Elizabeth Ave to Craythorne.				land owner.

14.	Try to keep existing shops/introduce new.		PC strongly objected to change of use of Old Post 							Office and Highfield Motors from commercial to 								residential.

15.	Doctor’s surgery.					It is understood that Rolleston will not have a 								surgery in the foreseeable future.  Have lobbied 								the PCT and Tutbury Practice.

16.	Install traffic calming on Church Road.			Completed.

17.	Expand recycling in the village.			All areas are now covered with ESBC recycling 								services.

18.	Set up network of Flood Wardens.			Six Flood Wardens are in place.  Still looking for 								two more.